| TASK (special activities are marked **) | SUBTASK | ROLE | START DATE | END DATE | PRODUCT (milestones are highlighted) | RESOURCES |
| --- | --- | --- | --- | --- | --- | --- |
| Project Launch( Stage II) |  |  | 10.feb.11 | 23.apr.11 | Poster theme project launched |  |
| Drawing scales for assessing the final presentation, poster, essay teamwork. |  | Teacher | 11.feb.11 | 14.feb.11 |  |  |
| Selection of working groups |  | Teacher | 12.febr.11 | 12.febr.11 | Groups | Computer word processing program, printer, paper or data storage media such as CDs, memory sticks, |
| Providing information class | Identifying appropriate transitions and animation effects to achieve a multimedia presentation |  | 13.feb.11 | 15-02-1011 | The class is made in the future project. Training class. | Plates, computers, video, network NetMeeting program, program performance capture stages for viewing multimedia presentation and website |
|  | Using the advanced settings to achieve a typical multimedia presentations. |  | 15.feb.11 | 17-02-1011 | Training class. | Plates, computers, video, network program netmetting |
|  | Description description structures structures logical functions arithmetic functions, statistical calculation of arithmetic functions, logical, statistical and financial accounting |  | 18.feb.11 | 28.feb.11 |  | Table, spreadsheet program, computers, working drawings, test done. |
|  | Function calculation and graphical representation of data obtained from field |  | 01.mar.11 | 04.mar.11 |  | Computer word processing program, image editing programs, video |
| Solving problems | Selection and preparation of data before being processed | Teacher | 05.mar.11 | 08.mar.11 |  |  |
|  | Specify the correct steps to achieve site creating accounts www.wiki.com site | Students | 09.mar.11 | 11.mar.11 | Solving problems | Computer spreadsheet program |
| Research / information on the Internet Search | Library | Researchers (students with reading skills) | 14.mar.11 | 15.mar.11 | Research Report | Access to the library |
|  | Online/ Encarta | Researchers (students with skills to navigate the Internet) | 15.mar.11 | 16.mar.11 |  | Computer permanent access to the Internet, |
|  | Writing research report | Writers of the report (students with writing skills) | 17.mar.11 | 17.mar.11 |  | Computer word processing program, printer, paper or data storage medium such as CD |
| Multimedia presentation, film and website for the “Young Environmentalist” (The causes, effects of massive deforestation, reforestation) |  |  | 18.mar.11 | 13.apr.11 | Overview |  |
|  | Presentation of case studies including graphics made presentation site | Each group | 18.mar.11 | 03.apr.11 |  | Computer program for making presentations |
|  | Introducing the class of the final products | Each group | 03.apr.11 | 13.apr.11 |  | Computer,video-projector |
| Assessment and grading |  |  | 18.mar.11 | 13.apr.2011 | Complete evaluation and assessment | Research Report |
|  | Preparation of fields | Teacher | 18.mar.11 | 03.apr.11 |  | Computer spreadsheet software, printer, paper |
|  | Evaluation | Teacher | 03.apr.11 | 13.apr.11 |  | Computer, printer tabular calculation program, paper |
| Reflection and Scoring |  |  | 13.apr.11 | 23.apr.11 | Complete reflection and scoring | Computer spreadsheet program, printer, paper |
|  | Ratings | Teacher | 13.apr.11 | 23.apr.11 |  | Computer, Microsoft Office, mprimantă, paper, video |
|  | Reflection and evaluation | Students | 03.apr.11 | 10.apr.11 |  |  |
| Project Completion |  | Teacher | 23.apr.11 |  |  |  |